## Overview
SmartCRM AI — Frontend Task Segregation Plan
Mapping the SRS to frontend-v1/, module by module. Planning reference only — no files in frontend-v1 were changed.
Source: SmartCRM AI SRS v1.0 (28-Jul-2026) ¦ Target repo: frontend-v1/ only ¦ Stack: React 19 + Vite + Zustand + Tailwind
Status legend
Status | Meaning
SCAFFOLDED | Route, permission gate and empty-state UI exist in frontend-v1 — needs data wiring, forms and detail views.
NOT STARTED | No folder exists yet in frontend-v1 — build from scratch.
LATER PHASE | Intentionally deferred: AI add-on tier or the separate mobile app.
Snapshot
Metric | Count | Note
Modules scaffolded | 9 | Shell + routing + RBAC done, feature logic pending
Modules not started | 2 | Communication Management (5), Sales Team Management (8)
AI capabilities deferred | 9 | Section 6.10 — own phase, chargeable add-on tier
Mobile app | 1 | Separate Flutter repository, not part of frontend-v1

## Modules
Modules
Every SRS module against its current state in frontend-v1.
No | Module | Primary Path | Status | FR / Section Refs | Description
01 | Customer Management (Customer 360°) | src/pages/customers/ | SCAFFOLDED | FR-1.1 – FR-1.7 | Single consolidated profile per customer: company details, contacts, purchase history, communication log and documents on one screen.
02 | Lead Management | src/pages/leads/ | SCAFFOLDED | FR-2.1 – FR-2.7 · BR-1, BR-2 | Capture-to-convert pipeline: New Lead -> Contacted -> Meeting -> Quotation -> Negotiation -> Converted.
03 | Sales Pipeline Management | src/pages/opportunities/ | SCAFFOLDED | FR-3.1 – FR-3.5 | Opportunities tracked through configurable stages with a kanban view showing cumulative deal value per stage.
04 | Quotation & Proposal Management | src/pages/quotations/ | SCAFFOLDED | FR-4.1 – FR-4.8 · BR-3 | Line-item quotations with a discount-approval gate and downloadable PDF proposals. AI drafting/pricing is a later phase.
05 | Communication Management | src/pages/communications/ (new folder) | NOT STARTED | FR-5.1 – FR-5.6 | Unifies Email, WhatsApp, SMS, call and meeting history into one timeline; also reused inside Customer 360°.
06 | Service & Support Management | src/pages/service/ | SCAFFOLDED | FR-6.1 – FR-6.5 | Complaint-to-resolution ticket flow with SLA timers per priority and post-close customer feedback.
07 | Marketing Management | src/pages/marketing/ | SCAFFOLDED | FR-7.1 – FR-7.7 | Campaign creation, segmentation, and promotion tracking. AI targeting/prediction is a later phase.
08 | Sales Team Management | src/pages/sales-team/ (new folder) | NOT STARTED | FR-8.1 – FR-8.5 | Targets, activity logging, attendance and commission — largely Sales-Manager-facing.
09 | Analytics Dashboard & Reporting | src/pages/reports/ & src/pages/dashboard/ | SCAFFOLDED | FR-9.1 – FR-9.7 · §18 | 7 role dashboards already exist with stat-card layout; Reports.jsx lists report categories gated by permission. Both need real chart data.
10 | Tenant Administration (Roles & Permissions) | src/pages/admin/ | SCAFFOLDED | §14 · §21.4 | User management, the read-only role matrix, and tenant settings. RBAC plumbing already exists and is used by every module above.
11 | Cross-Cutting AI Capabilities | src/components/ai/ & src/pages/ai/ (new) | LATER PHASE | §6.10 · FR-AI-1 – FR-AI-9 | Nine AI features attach as badges/panels onto the modules above, plus a standalone Chat Assistant. Sold as chargeable AI Premium tier.
12 | Sales Team Mobile App | separate repository — Flutter | OUT OF SCOPE | FR-M.1 – FR-M.6 | Shares the same backend APIs as this web app but is not part of frontend-v1 — its own repo/workstream.

## Tracks
Suggested Team Tracks
Five tracks sized for parallel work with minimal file overlap. Track 5 depends on the page shells from Tracks 1–4 existing first.
Track | Focus | Covers | Description | Primary Paths
Track 1 | Customer & Lead Core | Modules 1–2 | Customer 360° profile and the lead capture-to-qualify pipeline. The highest-traffic screens in the app — start here. | src/pages/customers/ ; src/pages/leads/ ; core/services/customer.service.js ; core/services/lead.service.js
Track 2 | Sales Pipeline & Quotations | Modules 3–4 | Opportunity kanban through to quotation PDF generation and the discount-approval gate (BR-3). | src/pages/opportunities/ ; src/pages/quotations/ ; core/services/opportunity.service.js ; core/services/quotation.service.js
Track 3 | Service, Communication & Marketing | Modules 5–7 | Unified inbox (new), service tickets with SLA badges, and campaign management. | src/pages/communications/ (new) ; src/pages/service/ ; src/pages/marketing/
Track 4 | Sales Team, Reporting & Admin | Modules 8–9, §14 | Targets/attendance/commission (new), the analytics dashboards, and tenant user/role administration. | src/pages/sales-team/ (new) ; src/pages/reports/ ; src/pages/dashboard/ ; src/pages/admin/
Track 5 | AI Layer & Cross-Cutting Infra | §6.10 + shared plumbing | Nine AI features (all deferred) plus shared plumbing every track needs: toasts, error shape, validation, date filters. | src/components/ai/ (new) ; core/services/ai.service.js (new) ; core/services/notification.service.js (new)

## Files
Files — existing vs. to build
Every file referenced by the plan, per module.
Module | File Path | Status | Note
01 Customers | src/pages/customers/Customers.jsx | EXISTS | List stub, permission-gated
01 Customers | src/pages/customers/CustomerDetail.jsx | NEW | Customer 360° tabbed view
01 Customers | src/pages/customers/CustomerForm.jsx | NEW | Create / edit
01 Customers | src/components/customers/ContactList.jsx | NEW | Multi-contact list
01 Customers | src/components/customers/PurchaseHistoryTable.jsx | NEW
01 Customers | src/components/customers/DocumentList.jsx | NEW | Upload / view / delete
01 Customers | src/components/customers/CommunicationTimeline.jsx | NEW | Shared with Module 5
01 Customers | src/core/services/customer.service.js | NEW | apiGet/Post/Put/Delete wrappers
02 Leads | src/pages/leads/Leads.jsx | EXISTS | List stub, permission-gated
02 Leads | src/pages/leads/LeadDetail.jsx | NEW
02 Leads | src/pages/leads/LeadForm.jsx | NEW
02 Leads | src/components/leads/LeadPipelineBoard.jsx | NEW | Kanban, 6 stages, drag-and-drop
02 Leads | src/core/services/lead.service.js | NEW
03 Opportunities | src/pages/opportunities/Opportunities.jsx | EXISTS | List stub, permission-gated
03 Opportunities | src/pages/opportunities/OpportunityDetail.jsx | NEW
03 Opportunities | src/pages/opportunities/OpportunityForm.jsx | NEW
03 Opportunities | src/components/opportunities/OpportunityKanban.jsx | NEW | Stage groups, cumulative value
03 Opportunities | src/components/opportunities/LossReasonModal.jsx | NEW | Required on Lost (FR-3.4)
03 Opportunities | src/core/services/opportunity.service.js | NEW
04 Quotations | src/pages/quotations/Quotations.jsx | EXISTS | List stub, permission-gated
04 Quotations | src/pages/quotations/QuotationDetail.jsx | NEW
04 Quotations | src/pages/quotations/QuotationForm.jsx | NEW | Line items, discount
04 Quotations | src/components/quotations/QuotationPdfPreview.jsx | NEW
04 Quotations | src/components/quotations/DiscountApprovalBanner.jsx | NEW | BR-3 gate
04 Quotations | src/core/services/quotation.service.js | NEW
05 Communications | src/pages/communications/Inbox.jsx | NEW | Unified Email/WhatsApp/SMS
05 Communications | src/pages/communications/CallLog.jsx | NEW
05 Communications | src/pages/communications/MeetingScheduler.jsx | NEW
05 Communications | src/components/communications/Timeline.jsx | NEW | Shared with Module 1
05 Communications | src/core/services/communication.service.js | NEW
05 Communications | src/core/constants/routes.constant.js | EXTEND | Add COMMUNICATIONS routes
05 Communications | src/core/constants/permission.constant.js | EXTEND | Add module + permission keys
05 Communications | src/components/sidebar/SidebarConfig.js | EXTEND | Add nav entry
06 Service | src/pages/service/ServiceTickets.jsx | EXISTS | List stub, permission-gated
06 Service | src/pages/service/TicketDetail.jsx | NEW
06 Service | src/pages/service/TicketForm.jsx | NEW
06 Service | src/components/service/SlaBadge.jsx | NEW | Needs SLA thresholds confirmed
06 Service | src/components/service/FeedbackForm.jsx | NEW | On ticket close
06 Service | src/core/services/ticket.service.js | NEW
07 Marketing | src/pages/marketing/Campaigns.jsx | EXISTS | List stub, permission-gated
07 Marketing | src/pages/marketing/CampaignDetail.jsx | NEW
07 Marketing | src/pages/marketing/CampaignForm.jsx | NEW
07 Marketing | src/components/marketing/SegmentBuilder.jsx | NEW
07 Marketing | src/core/services/campaign.service.js | NEW
08 Sales Team | src/pages/sales-team/Targets.jsx | NEW
08 Sales Team | src/pages/sales-team/Attendance.jsx | NEW | Web mirror of mobile FR-M.5
08 Sales Team | src/pages/sales-team/Commissions.jsx | NEW
08 Sales Team | src/pages/sales-team/ActivityLog.jsx | NEW
08 Sales Team | src/core/services/salesTeam.service.js | NEW
08 Sales Team | src/core/constants/permission.constant.js | EXTEND | SALES_TEAM module + TARGETS_VIEW/MANAGE
09 Reports | src/pages/reports/Reports.jsx | EXISTS | Category cards, permission-gated
09 Reports | src/pages/dashboard/*.jsx | EXISTS | 7 role dashboards, stat cards stubbed
09 Reports | src/pages/reports/SalesReport.jsx | NEW
09 Reports | src/pages/reports/RevenueReport.jsx | NEW
09 Reports | src/pages/reports/ServiceReport.jsx | NEW
09 Reports | src/pages/reports/CampaignPerformanceReport.jsx | NEW
09 Reports | src/components/common/DateRangeFilter.jsx | NEW | Shared with Module 2/3 kanban filters
09 Reports | src/core/services/report.service.js | NEW
10 Admin/RBAC | src/pages/admin/Users.jsx | EXISTS | Needs real invite flow
10 Admin/RBAC | src/pages/admin/Roles.jsx | EXISTS | Read-only role matrix
10 Admin/RBAC | src/pages/admin/Settings.jsx | EXISTS | Needs pipeline/SLA/discount config panels
11 AI Layer | src/pages/ai/ChatAssistant.jsx | NEW | FR-AI-4
11 AI Layer | src/components/ai/LeadScoreBadge.jsx | NEW | FR-AI-1, on Leads
11 AI Layer | src/components/ai/ForecastPanel.jsx | NEW | FR-AI-2, on dashboards/reports
11 AI Layer | src/components/ai/RecommendationCard.jsx | NEW | FR-AI-3, on Customers
11 AI Layer | src/components/ai/AiDraftBadge.jsx | NEW | FR-AI-5, distinguishes AI content (BR-6)
11 AI Layer | src/components/ai/SentimentTag.jsx | NEW | FR-AI-6, on Customers
11 AI Layer | src/components/ai/CoachingPanel.jsx | NEW | FR-AI-8, on Sales Executive dashboard
11 AI Layer | src/components/ai/DuplicateMergeModal.jsx | NEW | FR-AI-9, on Customers
11 AI Layer | src/core/services/ai.service.js | NEW
Infra | src/core/services/notification.service.js | NEW | Toast dispatcher
Infra | src/components/common/Toast.jsx | NEW
Infra | src/core/services/interceptor.service.js | EXTEND | Standardized error shape + correlation ID (§16)
Infra | src/core/utils/validation.js | EXTEND | File size/type, discount 0–100%, dup-name hook (§15)

## Tasks
Build tasks
Concrete tasks per module, drawn from the SRS functional requirements.
Module | Task | FR / Section Ref
01 Customers | Customer list with search/filter by industry, account status | FR-1.1
01 Customers | Customer 360° view: profile + contacts + purchase history + comms timeline + documents in one page | FR-1.7
01 Customers | Document upload with type/size validation | FR-1.5 · §15
01 Customers | Industry classification dropdown (configurable list) | FR-1.6
02 Leads | Kanban board across the 6 pipeline stages, drag-and-drop | FR-2.4 · §11.1
02 Leads | Stage-order enforcement with logged manual override | BR-1
02 Leads | Follow-up reminder scheduling, tied to notification.service.js | FR-2.5
02 Leads | Convert action auto-creates linked Customer + Opportunity | BR-2 · FR-2.6
03 Opportunities | Kanban grouped by stage, cumulative value per column | FR-3.3
03 Opportunities | Required loss-reason capture before closing as Lost | FR-3.4
03 Opportunities | Team + individual performance summary view (feeds Sales Manager dashboard) | FR-3.5
04 Quotations | Line-item form: qty x unit price, discount % (0-100) | §15
04 Quotations | Block send when discount > threshold until approver confirms | BR-3 · FR-4.3
04 Quotations | PDF generation with branding | FR-4.4
04 Quotations | Response tracking: Pending / Viewed / Approved / Rejected / Expired | FR-4.5
04 Quotations | Reserve a slot for the future AI-draft button — do not build yet | FR-4.6 (later)
05 Communications | Unified inbox: Email / WhatsApp / SMS in one list | FR-5.1, 5.2
05 Communications | SMS alert log for configurable events | FR-5.3
05 Communications | Manual call-log entry with outcome + notes | FR-5.4
05 Communications | Meeting scheduler with reminders | FR-5.5
05 Communications | Single chronological timeline component, reused on Customer 360° | FR-5.6
06 Service | Priority + status workflow (Open -> Assigned -> In Progress -> Resolved -> Closed) | FR-6.2
06 Service | SLA badge/escalation flag once threshold values are confirmed | FR-6.4 (see Open Questions)
06 Service | Feedback capture on closure, feeding Service reports | FR-6.5
07 Marketing | Campaign create/schedule/launch form | FR-7.1
07 Marketing | Segment builder: industry, purchase history, engagement, lead source | FR-7.2
07 Marketing | Performance metrics view: sent / opened / clicked / converted | FR-7.4
08 Sales Team | Target setting per salesperson/team for a defined period | FR-8.1
08 Sales Team | Attainment display against target | FR-8.2
08 Sales Team | Activity log: calls, visits, meetings, quotations sent | FR-8.3
08 Sales Team | Attendance check-in/out (web mirror of mobile FR-M.5) | FR-8.4
08 Sales Team | Commission calculation display from configurable rules | FR-8.5
09 Reports | Wire dashboard stat cards to real aggregate data, scoped by role (own/team/all) | FR-9.1, 9.6
09 Reports | Date-range + team + individual filters, respecting §14 scoping | FR-9.6
09 Reports | PDF/XLSX export action per report | §18.1
09 Reports | Chart components — consult the dataviz design skill before building any chart
10 Admin/RBAC | Users.jsx: real invite flow + list backed by the user API | §14
10 Admin/RBAC | Settings.jsx: pipeline stage config, SLA thresholds, discount threshold | §13, §21.4 (pending answers)
10 Admin/RBAC | Confirm whether the role matrix becomes per-tenant configurable | §25.4 Q6

## AI Features
AI feature -> attachment point
All nine AI capabilities (§6.10), later phase, and where each attaches once built.
AI Feature | FR Refs | Attaches To | Component
AI Lead Scoring | FR-AI-1.1 – 1.3 | pages/leads/ | LeadScoreBadge.jsx
AI Sales Prediction | FR-AI-2.1 – 2.3 | dashboard/, reports/ | ForecastPanel.jsx
AI Customer Recommendation | FR-AI-3.1 – 3.3 | pages/customers/ | RecommendationCard.jsx
AI Chat Assistant | FR-AI-4.1 – 4.4 | pages/ai/ChatAssistant.jsx | standalone page
AI Email & Message Generator | FR-AI-5.1 – 5.3 | quotations/, communications/ | AiDraftBadge.jsx
AI Customer Sentiment Analysis | FR-AI-6.1 – 6.3 | pages/customers/ | SentimentTag.jsx
AI Meeting Assistant | FR-AI-7.1 – 7.3 | communications/MeetingScheduler.jsx | MeetingSummaryPanel.jsx
AI Sales Coach | FR-AI-8.1 – 8.3 | dashboard/SalesExecutiveDashboard.jsx | CoachingPanel.jsx
AI Duplicate Customer Detection | FR-AI-9.1 – 9.4 | pages/customers/ | DuplicateMergeModal.jsx

## Open Questions
Open questions before building forms
Carried over from SRS §25.4 — the subset that changes what a screen actually looks like.
# | Question | SRS Ref | Impacts
1 | Discount approval threshold value and approver hierarchy | SRS §6.4 / §13 | Blocks final UI for DiscountApprovalBanner.jsx (Module 4)
2 | SLA duration per ticket priority, and whether it varies by industry | SRS §6.6 | Blocks SlaBadge.jsx (Module 6)
3 | Should the role/permission matrix be customizable per tenant, or fixed as shipped? | SRS §14 | Changes whether Roles.jsx stays read-only or becomes an editor
4 | Is a customer-facing self-service portal in scope this phase? | SRS §2.3 | If yes, a 13th, publicly-routed module outside this plan
5 | Starter/Business/Enterprise feature-gating boundaries | SRS §2.1 | Determines whether Module 5 (Communication) and Module 11 (AI) need a plan-based feature flag now or later

## Backend Note
Backend coordination note
Informational only — no action for this frontend plan, but worth flagging to whoever owns backend-v1.
Package mismatch: backend-v1 (Spring Boot) currently exposes customer, lead, quotation, employee, attendance, payroll, leave, project, task, invoice packages. It has no opportunity, service-ticket, or campaign module yet, and carries HR-style packages (payroll, leave) the SRS doesn't call for. Modules 3, 6 and 7 in this plan will need matching API work before their forms can go past static/mock data.
Backend packages present today
Present
attendance
audit
auth
customer
dashboard
department
designation
employee
file
invoice
lead
leave
notification
payment
payroll
project
quotation
report
setting
task
user
Missing vs. this plan's frontend modules
Missing
opportunity (Module 3)
service-ticket (Module 6)
campaign (Module 7)
sales-team target/commission (Module 8, partial overlap with payroll)

## Directory Tree
Proposed folder structure
src/ — existing paths plus every new path proposed by this plan.
Path | Status | Note
src/core/constants/ | EXISTS | app.constant.js, permission.constant.js, routes.constant.js, …
src/core/hooks/ | EXISTS | useAuth.js, usePermissions.js
src/core/services/api.service.js | EXISTS
src/core/services/auth.service.js | EXISTS
src/core/services/storage.service.js | EXISTS
src/core/services/interceptor.service.js | EXISTS
src/core/services/customer.service.js | NEW | Module 1
src/core/services/lead.service.js | NEW | Module 2
src/core/services/opportunity.service.js | NEW | Module 3
src/core/services/quotation.service.js | NEW | Module 4
src/core/services/communication.service.js | NEW | Module 5
src/core/services/ticket.service.js | NEW | Module 6
src/core/services/campaign.service.js | NEW | Module 7
src/core/services/salesTeam.service.js | NEW | Module 8
src/core/services/report.service.js | NEW | Module 9
src/core/services/ai.service.js | NEW | AI layer
src/core/services/notification.service.js | NEW | Cross-cutting
src/core/utils/ | EXISTS | permission.js, validation.js, axios.js
src/components/common/, sidebar/, dashboard/ | EXISTS
src/components/customers/ | NEW | ContactList, PurchaseHistoryTable, DocumentList, CommTimeline
src/components/leads/ | NEW | LeadPipelineBoard (kanban)
src/components/opportunities/ | NEW | OpportunityKanban, LossReasonModal
src/components/quotations/ | NEW | QuotationPdfPreview, DiscountApprovalBanner
src/components/communications/ | NEW | Timeline, CallLogForm, MeetingScheduler
src/components/service/ | NEW | SlaBadge, FeedbackForm
src/components/marketing/ | NEW | SegmentBuilder, CampaignPerformanceChart
src/components/ai/ | NEW | LeadScoreBadge, ForecastPanel, SentimentTag, CoachingPanel, …
src/pages/customers/Customers.jsx | EXISTS | scaffolded list
src/pages/customers/CustomerDetail.jsx, CustomerForm.jsx | NEW
src/pages/leads/Leads.jsx | EXISTS | scaffolded list
src/pages/leads/LeadDetail.jsx, LeadForm.jsx | NEW
src/pages/opportunities/Opportunities.jsx | EXISTS | scaffolded list
src/pages/opportunities/OpportunityDetail.jsx, OpportunityForm.jsx | NEW
src/pages/quotations/Quotations.jsx | EXISTS | scaffolded list
src/pages/quotations/QuotationDetail.jsx, QuotationForm.jsx | NEW
src/pages/communications/ | NEW | Module 5 — Inbox.jsx, CallLog.jsx, MeetingScheduler.jsx
src/pages/service/ServiceTickets.jsx | EXISTS | scaffolded list
src/pages/service/TicketDetail.jsx, TicketForm.jsx | NEW
src/pages/marketing/Campaigns.jsx | EXISTS | scaffolded list
src/pages/marketing/CampaignDetail.jsx, CampaignForm.jsx | NEW
src/pages/sales-team/ | NEW | Module 8 — Targets.jsx, Attendance.jsx, Commissions.jsx, ActivityLog.jsx
src/pages/reports/Reports.jsx | EXISTS | scaffolded categories
src/pages/reports/SalesReport.jsx, RevenueReport.jsx, ServiceReport.jsx, … | NEW
src/pages/dashboard/*.jsx (7 role dashboards) | EXISTS
src/pages/finance/Approvals.jsx | EXISTS
src/pages/admin/Users.jsx, Roles.jsx, Settings.jsx | EXISTS
src/pages/ai/ | NEW | ChatAssistant.jsx
src/pages/common/Profile.jsx, Unauthorized.jsx, NotFound.jsx | EXISTS